## Project
Project Overview
Project Name | iOS App Lineup
Project Manager | Murapyon
Description
Start date (read-only) | 2024-10-31
Finish date (read-only) | 2024-12-01
Duration (read-only) | Pro only
Progress (read-only) | 9.1%
Work (read-only) | Pro only
Cost (read-only) | Pro only

## Tasks
[8 empty] | October 2024 |  |  |  |  | November 2024 | [29 empty] | December 2024 | [30 empty] | January 2025 | [30 empty] | February 2025 | [27 empty] | March 2025
20 | WBS | Task description | PR | PIC | Start date | Finish date | Progress | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[8 empty] | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa
1 | 1 | アプリケーション設計 | 11 |  | 2024-10-31 | 2024-11-10 | 9.1% | bar: Th to Su
12 | 1.1 | テーマ策定 | 1 | Murapyon | 2024-10-31 | 2024-10-31 | 100% | bar: Th; Su
14 | 1.2 | 機能一覧 | 10 | Murapyon | 2024-11-01 | 2024-11-10 | 0% | bar: Fr to Su
10 | 1.3 | バックエンド設計 |  |  |  |  | 0% | bar: Su
15 | 1.3.1 | ER図 |  | Murapyon |  |  | 0% | bar: Su
16 | 1.3.2 | テーブル定義書 |  | Murapyon |  |  | 0% | bar: Su
17 | 1.3.3 | アプリケーション定義書 |  | Murapyon |  |  | 0% | bar: Su
5 | 1.4 | フロントエンド設計 |  |  |  |  | 0% | bar: Su
18 | 1.4.1 | 画面遷移図 |  | Murapyon |  |  | 0% | bar: Su
19 | 1.4.2 | ワイヤーフレーム |  | Murapyon |  |  | 0% | bar: Su
20 | 1.4.3 | アプリケーション定義書 |  | Murapyon |  |  | 0% | bar: Su
Note on I2: Product Requirements：工数(人日)
Note on J2: Person In Charge：担当者

## 機能一覧
項目 | 機能名 | 作成する上での優先順位 | 難易度 | 概要 | 参考サイトもしくはアプリ | 実装予定機能 | 実装済機能